## Sept 16-20
MY SHEET
Activity | Date-Time-Start | Date-Time-End | Remarks
Proposal of Systems | September 16 1:00pm | September 20 1:00pm
Research about their Proposal | September 16 1:00pm | September 20 1:00pm

## Sept 23-30
MY SHEET
Activity | Date-Time-Start | Date-Time-End | Remarks
Making a Survey for the Accepted Proposal | September 23 1:00pm | September 24 5:00pm
Surveying all possible client | September 25 8:00am | September 25 3:00pm
Brainstorming Ideas | September 26 1:00pm | September 26 3:00pm
Brainstorming Ideas part 2 | September 27 1:00pm | September 27 3:00pm

## Sep.30- Oct.4
MY SHEET
Activity | Date-Time-Start | Date-Time-End | Remarks
Applying ideas to technical | September 30 1:00pm | September 30 3:00pm
Making a content in the system | October 1 1:00pm | October 3 5:00pm
Searching a connection to database | October 4 1:00pm | October 4 5:00pm